## Sheet1
Project X - Automated Attendance System
Task ID | Task Name | Sub Task ID | SubTask Name | Deliverables | Estimated Hours | Assignee | Start Date | End Date | Status | Actual Hours Spent | Notes
1 | Project Initiation | 1.1 | Project Kickoff Meeting |  | 2 | Roberto Prisoris | 2025-02-27 | 2025-02-27 | Done | 2
|  | 1.2 | Identifying Project Scope & Objectives | Updated Requirements Review | 8 | Jenny Babe Arac | 2025-02-28 | 02-29-2025 | Done | 7
2 | Requirement Analysis | 2.1 | Gather Functional Requirement | Project X - Client Stated Requirement | 6 | Kit Adrian Diocares | 2025-03-01 | 2025-03-01 | Done | 8
|  | 2.2 | Initiate an Elicitation Session with Client | Project X - Requirements Elicitation - v.1.0 | 4 | Shannen Mendoza | 2025-03-03 | 2025-03-05 | Done | 3
|  | 2.3 | Validate Requirements with Client | Project X - Requirements Elicitation - v.1.1 | 3 | Jenny Babe Arac | 2025-03-06 | 2025-03-06 | Done | 3
|  | 2.4 | Finalizing System Requirements | Project X - Requirements Elicitation - v.1.2 | 3 | Shannen Mendoza | 2025-03-07 | 2025-03-07 | Done | 3
3 | High-Level Design | 3 | Conceptual Design | High-Level Use Case Diagrams, Conceptual Model Requirement Diagrams Project Plan | 10 | Kit Adrian Diocares, Roberto Prisoris, Jenny Babe Arac | 2025-03-08 | 03- 08-2025 | Ongoing | 12
4 | Detailed Design | 4.1 | Develop Class Diagram | Class Diagram with Attributes & Methods | 4 | Kit Adrian Diocares | 2025-03-10 | 2025-03-10 | Pending
|  | 4.2 | Sequence Diagram | At least one detailed Sequence Diagram | 6 | Jenny Babe Arac | 2025-03-11 | 2025-03-11 | Pending
|  | 4.3 | Activity Diagram | Activity Diagrams for Key System Processes | 6 | Shannen Mendoza | 2025-03-12 | 2025-03-12 | Pending
5 | Documentation & Version Control | 5 | Set up Version Control (Git) | Git Repository Setup Provide Access to Repository | 2 | Roberto Prisoris | 2025-03-14 | 2025-03-14 | Done | 1
6 | Agile Development Process | 6.1 | Sprint Planning | Sprint Backlog Development Roadmap | 8 | Roberto Prisoris | 2025-03-17 | 2025-03-19 | Pending
|  | 6.2 | Daily Standups | Recording Progress Updates | 10 | Kit Adrian Diocares | 2025-03-20 | 2025-03-22 | Pending
|  | 6.3 | Sprint Demonstration to Client | Sprint Review, Working Feature Demostration | 10 | Jenny Babe Arac | 2025-04-02 | 2025-04-04 | Pending
7 | Test-Driven Development (TDD) | 7 | Develop & Test a Module using TDD | Test Cases, Unit Tests TDD Implementation | 24 | Roberto Prisoris | 2025-04-07 | 2025-04-09 | Pending
8 | Implementation | 8.1 | Develop Authentication | Secure API, OTP Authentication, QR Validation | 30 | Roberto Prisoris | 2025-04-10 | 2025-04-15 | Pending
|  | 8.2 | Implement Role-based Access Control | Admin, Instructor, Student Access System | 12 | Kit Adrian Diocares | 2025-04-16 | 2025-04-18 | Pending
|  | 8.3 | Attendance Tracking Features | QR Code Scanner, GPS Validation | 18 | Roberto Prisoris | 2025-04-19 | 2025-04-20 | Pending
|  | 8.4 | Cloud Database Integration | Hosted Database, Secure APIs | 12 | Jenny Babe Arac | 2025-04-21 | 2025-04-23 | Pending
9 | Testing & Validation | 9.1 | Unit Testing | Verified Functionality of Individual Components | 12 | Shannen Mendoza | 2025-04-24 | 2025-04-25 | Pending
|  | 9.2 | System Testing | Full System Integration Test | 24 | Shannen Mendoza | 2025-04-26 | 2025-04-28 | Pending
|  | 9.3 | User Acceptance Testing (UAT) | Client Validation & Feedback | 4 | Jenny Babe Arac | 2025-04-29 | 2025-04-29 | Pending
10 | Final Demonstration & Handover | 10.1 | Final System Review | Working Code, Documentation, User Manual | 10 | Kit Adrian Diocares | 2025-04-30 | 2025-05-01 | Pending
|  | 10.2 | Final Presentation | Project Presentation, Live Demo | 4 | Team A | 2025-05-02 | 2025-05-02 | Pending